## DailyBoard
To Do | In Progress | Completed | Comments
As a PhD Intern, I would like to understand and explore the kaggle competion, so that I have clear understaing of the project Strory points: 2 Start Date: 19/07/2024 End Date: 22/07/2024 | To explore the Kaggle competition project, I enrolled in two modules on Coursera: 1. Generative AI with Large Language Models 2. Generative AI for Everyone 3. Building Applications with Vector Databases | I have completed the following two courses on Coursera: 1. Generative AI with Large Language Models 2. Generative AI for Everyone | Coursera courses provided a solid foundation in generative AI, which is vital to the Kaggle competition. With the completion of these courses, I am more confident in my ability to approach the project.
As a PhD Intern, I would like to create a design of how to solve the kaggle competion project, so that I have a plan for solution implementation Strory points: 2 Start Date: 23/07/2024 End Date: 24/07/2025 Output: Diagram for implementation plan | Currently, I am designing a detailed implementation plan for the Kaggle project. This involves outlining the steps and identifying necessary resources for each phase of the project. | The implementation plan for the Kaggle project includes: 1. Diagram for the overall workflow and architecture. | The design phase is progressing well. I have outlined the major components required for the solution, including the data preprocessing pipeline, model selection and training strategy, and evaluation metrics. These components help me in the subsequent implementation phases and ensure a structured approach to solving the Kaggle competition project.
As a PhD Intern, I would like to write code for the kaggle competion, so that I can implement my solution Strory points: 5 Start Date: 25/07/2024 End Date: 31/07/2026 Output: Metric score achieved | I am implementing the Kaggle dataset using OpenAI API with GPT-3.5 Turbo, employing both the basic approach and prompt engineering. I generated the OpenAI API keys and explored various prompt structures to figure out the most suitable approach for achieving better accuracy. | I implemented the Kaggle dataset using OpenAI API with GPT-3.5 Turbo, employing both the basic approach and prompt engineering. The accuracy achieved was 61% and 73%, respectively. The basic approach uses simpler prompts and allows some randomness in responses with a temperature setting of 0.5. Prompt engineering involves more detailed instructions, deterministic responses with a temperature setting of 0, and limits response length to avoid additional text. I have completed and presented the report titled 'TCS_Kaggle Project Report.' The presentation has been shared as a PowerPoint file named 'TCS_Kaggle_Project_Report.pptx' in the GitHub repository 'TCS-Kaggle-LLM-Science-Project. | Progress Update: I prepared and presented the report titled 'TCS_Kaggle Competition Project Report.' The feedback from my mentors was positive and very constructive. They provided valuable insights that I will incorporate moving forward. My next step is to focus on increasing the accuracy of the model using the GPT family, with a particular emphasis on refining prompt engineering and optimizing model parameters.
As a PhD Intern, I would like to review top solutions on kaggle, so that I can identify the gaps on my solution Strory points: 2 Start Date: 01/08/2024 End Date: 02/08/2027 Output: Document containing gaps in implementation and top strategies used (minumum 3) using top solutions on Kaggle | I am exploring to review the top solutions on Kaggle to identify gaps in my current implementation and adopt top strategies used by others. | Team H2O LLM Studio (1st Place Solution)Method:​ Utilized a combination of various language models including OpenAI's GPT-4 to achieve the highest accuracy. ​ Employed techniques such as fine-tuning pre-trained models on specific domains and ensembling multiple models to improve performance. ​ For example, the use of RoBERTa and DeBERTa v3 models ​ Leveraged data augmentation and preprocessing strategies to enhance the quality and quantity of training data. ​ Applied advanced hyperparameter tuning and optimization methods to find the best configurations for the models. ​ For example: Grid Search and Random Search, Optuna, Early Stopping​ Hardware Used:​ High-performance GPUs were used to train and fine-tune the models, likely including NVIDIA A100s or V100s.​ Leveraged cloud-based solutions to access the necessary computational resources for large-scale model training.​ Accuracy: 93.32% (Single Model), 93.33% (Winning Kernel) | Our approach, inspired by Team H2O LLM Studio's 1st place solution, utilized advanced language models and optimization techniques. Key methods and challenges have been detailed in the presentation titled 'Top Solution and Gaps MCQ Kaggle.pptx,' which is available in the repository.
As a PhD Intern, I would like to integrate top stratgeies in my solution, so that I can improve upon my initial metrics achieved. Strory points: 3 Start Date: 05/08/2024 End Date: 08/08/2028 Output: Metric score achieved | I am currently exploring methods to further increase the accuracy of the model. This involves experimenting with additional hyperparameters, testing alternative models, and refining the existing approach to push the accuracy even higher. | We followed the top solution techniques but, due to certain limitations, not all methods were implemented. We explored an Optuna-based GPT-4 model and achieved an accuracy of 86% with a temperature setting of 0.8743. The detailed analysis and results are documented in the notebook available on the GitHub repository. | While we achieved significant improvements using the Optuna-based GPT-4 model, there is potential for further optimization. Future work could involve experimenting with additional hyperparameters or exploring alternative models to push the accuracy even higher. Feedback from this phase has been positive from the mentors.

## Retrospective1
2024-07-31
What did we do well | What can be done better | Action Items

## Retrospective2
2024-08-09
What did we do well | What can be done better | Action Items